Subject Action Plan: Physical Education

Document Control

| This document has been approved for operation within: | Weeton St Michael’s C of E School |
| --- | --- |
| Date of last review | September 2024 |
| Date of next review | September 2025 |
| Review period | Yearly |
| Status | V2 |
| Owner | Emily Bickerstaffe |
| Version | 1 |

| Objective | Actions | Lead | Date | Termly RAG |
| --- | --- | --- | --- | --- |
| Build on the Lancashire PE Passport curriculum so that it meets the needs of mixed age teaching and the large number of SEND pupils. (Intent and Implementation) | - Adapt the curriculum so that it meets the needs of the pupils - Deliver training to staff (teachers and TAs) - Develop a guide and staff training for new/supply staff - Resource the adapted curriculum using OPAL funding and PE funding - Ensure that all documentation and resources are available via the PE resource shed and on-line resources - Develop the PE progression document and ensure staff are familiar with it - Finalise the reading curriculum statement (intent, implementation and impact) - Staff will use floor books (with assessment resources) to evidence pupils’ developing knowledge and skills | EB EB EB EB EB EB EB EB | Sept 2024 Sept 2024 Sept 2024 May 2024 Sept 2024 Sept 2024 Mar 2024 Pilot summer term with Oak Class with a view to all classes from Sept 2024 |  |
| Ensure parents are familiar with the curriculum and can support pupil engagement with physical activity and sport | - A curriculum MAT and progression documents will be available for parents/ carers to understand what children are learning - Increase engagement in physical activity and sport through promoted extra-curricular activity - Utilise PP funding to enable disadvantaged pupils to access sport and physical activity | EB EB EB | Ongoing June 2024 Ongoing |  |
| Ensure accurate assessment of the curriculum | - Observe PE teaching to ensure effective implementation and assessment - Internal moderation of PE floor books (including knowledge and skills progression) and summative data and report to SLT and governors - Establish a moderation cluster - Pupil interviews to test retrieval, enjoyment and wider participation outside of schools | EB EB EB EB EB | June 2024 Annually Termly Sept 2024 Termly |  |
| SEND pupils make progress | - Ensure that floor book resources support teachers to make adaptations - Staff and parents will implement pupil passport actions and ensure that adaptations are made - Specialist teachers will influence strategies/ resources for SEND pupils | EB/SENDco EB/ SENDco EB/ SENDco | Sept 2024 Ongoing/ half termly review Annually for each pupil |  |
| Pupils develop a knowledge and understanding of being healthy | - Create and deliver an assembly each term to promote healthy lifestyle - Create an accessible PE display (using PE funding) for parents and pupils to promote opportunities, healthy recipes - Developing sports day to promote healthy snacks e.g. fruit kebabs, fruit iced lollies | Staff EB Staff | Termly June 2024 June 2024 |  |
| The curriculum is reviewed so that learning is maximised | - PE report written for all stakeholders with recommendations | EB | July 2024 |  |
| Evaluation of impact of actions to date |  |  |  |  |